## PFM_PIO_TA_ActionPlan2021-2022
PFM Area (Component of PFM Action Plan) | Reference to concreat Measure in PFM Action Plan |  | Intended Activity | Timeframe | [5 empty] | Input |  |  | Expected outputs/ outcomes | Overlaps (Yes/No) | Difference between PIOs TA suggestions B/A PFM DCM | Questions to be discussed with PIOs
|  | PIO |  | 2021 |  | 2022 |  |  |  | Local consultancy | International consultancy | Other (specify)
|  |  |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1. Macroeconomic and Budget Indicators Forecasting | 1.2. Introduction and full-fledged launch of DSGE model(s) | RF MOF | Revenue forecasting methodology development | X | X | X | X | X | X |  | X |  | Methodology of revenue forecasting development | NO | The TA for the measure is suggested by RF MOF. The measure wasn't included in MoF TA needs intial list.
|  |  | Introduction of DSGE model |  |  | X | X | X | X |  | X |  | Completion of introduction of DSGE model | NO | The TA for the measures are suggested by RF MOF. The measures weren't included in MoF TA needs initial list.
| 3.1. Implementation of measures aimed at development of capacities, enhancement of skills of the personnel |  | Capacity building | X | X | X | X | X | X |  | X |  | Skills of application of the revenue forecasting model within RA MoF | NO
2 Fiscal risks accountability | 4․1 Expanding the coverage of fiscal risk assessment, improving the methodology | IMF | TA on fiscal risks, which could also cover PIM, monitoring the progress of the activities within the Stand-By Agreement (SBA) program discussions |  | X | X |  |  |  |  | IMF Staff and Short term experts |  | The scope of fiscal risk assessment is expanded and methodology is improved | NO | The IMF TA suggestion for the measure is expanded and could also cover PIM
|  | ADB1* | 1.Provide training support and advisory inputs on Fiscal Risk Assessment and on adoption of FRM Framework roadmap |  | X | X | X |  |  | TBD | TBD |  | (i) conduct of at least 2 workshops on FRA and FRM; (ii) guidelines | NO | The ADB TA suggestion for the measure is detailed compared to the initial suggestion and includes FRM Framework roadmap
|  |  | 2.Develop methodological guidelines |  |  | X | X
| 5․1 Capacity building | ADB1* | [11 empty] | NO
3․ State revenue policy | 6․1 Outline of main directions of further reforms in the tax system based on economic development priorities and opportunities | RF MOF | Support in tax policy changes for investment- and innovation-intensive growth | X | X | X | X | X | X |  | X |  | To be agreed with the RA MOF | NO | The TA for the measure is suggested by RF MOF. The measure wasn't included in MoF TA needs initial list.
| 7.1 Elaboration of the RA draft law "On Making Amendments to the RA Tax Code" | ADB | 1. Package or design next phase of technical assistance | X | X |  |  |  |  | TBD | TBD |  | Proposed amendments to the Tax Code (i) unified alternative tax system to replace the turnover tax regime, (ii) mnitoring and reporting framework for tax expenditures, and (iii) thin capitalization rules (based on best international practices). | NO | The TA for the measure is suggested by ADB based on the agreements with MoF Revenue Policy and Administration Methodology Department
| 8․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" |  | 2.Organize workshops or FGDs to gather information |  | X
|  |  | 3.Review of existing laws, amendments and supplements |  |  | X | X
|  |  | 4. Provide policy guidance on legal, regulatory and institutional framework for implementation |  |  |  | X | X
|  |  | 5. Submit draft amendments to the RA law and draft roadmap on implementation specific to turnover tax regime, tax expenditure and thin capitalization rules. |  |  |  |  | X | X
4. Revenue Transparency and Compliance | 12․1.Assess tax potential and tax gap for three major types of taxes (VAT, profit tax, income tax) | IMF | TA on calculation of VAT Gap | X | X | X |  |  | X |  | IMF Staff and Experts |  | Improved understanding of noncompliance and where to target resource | NO | The TA for the measures is suggested by IMF. The measures weren't included in MoF TA needs initial list.
| 15.1. Modernize analytical and control tools and improve capacities of tax authority | IMF | TA on implementing CRM (Compliance risk managment) | X |  | X |  | X | X |  | IMF Staff and Experts |  | Improved tax revenue from better targeting of noncompliance | NO
|  |  | TA on audits using IAM (Identity and Access Management) |  |  |  | X |  |  |  | IMF Staff and Experts |  | Improved tax revenue | NO
|  |  | TA on implementing Universal PIT Declaration | [5 empty] | X |  | IMF Staff and Experts |  | Improved compliance | NO
|  |  | TA on mobilizing taxes from multinational enterprises | [5 empty] | X |  | IMF Staff and Experts |  | Improved tax revenue from multinational enterprises | NO
5. Program budgeting and strategic planning | 16․1․ Review/develop budget programs in line with policies being carried out by existing strategic documents | IMF | TA on aligning budgetary framework with the strategic planning framework |  |  |  |  | X | X |  | Short term experts |  | Budgetary framework is aligned with the strategic planning framework | Overlaps IMF/UNDP | The mission will take place depending on demand and resource availability | Support scope needs to be clarified
|  | UNDP | Support MoF in studying / evaluating the compliance of budget programs with the policies defined by the strategic documents | X | X |  |  |  |  | X |  | As required workshops, engagement of other local or international experts can be provided. | Draft report of findings from the study (inventory and mapping of existing policy and budget frameworks, policy-budget link analysis and recommendations, etc). |  | The scope of TA suggestion is limited compared to the UNDP initial TA suggestion, cutting off the support to the State bodies to review policy documents and budget programs and their inter-compliance.
|  | RF MOF | Analysis of strategic documents with a view of identifying linkages with budget programs of line ministries | X | X | X | X | X | X |  | X |  | To be agreed with the RA MOF |  | The TA suggestion from RF MOF is detailed
| 16․2 Identification and regulation of practical issues related to program budgeting existing methodology and its application | GIZ | Support to MTAI and MOF in making PB mandatory for local level (based on similar experience from central level): legal amendments, final review and harmonisation of methodologies, creation of a cooperation platform between all stakeholders. | X | X | X |  |  |  | X |  |  | PB is a mandatory classification for local budgets: legal changes have been approved, methodological frameworks of state and local budgets on PB are fully harmonised | NO | The TA suggestion is detailed by GIZ
|  | IMF1* | TA on program budgeting framework (classification, evaluation guidelines) |  |  |  |  | X | X |  | Short term experts |  | Budget program evaluation guidelines are developed and budget program evaluation system is introduced |  | The mission will take place depending on demand and resource availability | Support scope needs to be clarified
|  | RF MOF | Review and analysis of the methodological guidelines for the development of sectoral strategies from the perspective of program budgeting, | X | X | X | X | X | X |  | X |  | To be agreed with the RA MOF |  | The TA suggestion from RF MOF is detailed
| 16․3․ Measures for human resources development | IMF1* | [13 empty] | Support scope needs to be clarified
|  | WB | Ongoing regional level support through PEMPAL regional project | X | X | X | X | X | X |  |  | knowledge sharing, learning about the good practices and experience of advanced countries | MoF relevant staff have access to knowledge related to the topic, have better understanding of international good practices | NO | WB initial TA suggestion didn't consider support for this measure implementation
| 17․2․ Introduce a process of regular evaluation of budget programs | GIZ | Piloting and finalisation of the concept and methodology on Programme Monitoring and Evaluation, including also capacity development activities. | X | X | X | X |  |  | X |  |  | State Budget Programmes' M&E concept and methodology are finalised, relevant capacities are developed in public institutions | NO | The TA suggestion is detailed by GIZ
6. MTEF process, budget disciplinary and transparency | 19.1. Developing legal framework and methodology for a unified procedure of MTEF and annual budget development | IMF | 1. TA on piloting the revised mandatory/ discretionary distinction 2.TA on budget preparation (CCAMTAC) | X | [6 empty] | Short term experts/Short term experts and long term experts (CCAMTAC/3) |  | Revised mandatory/discretionary distinction implemented leading to improved expenditure flexibility and increased fiscal space | NO | The TA for the measures is suggested by IMF. The measures weren't included in MoF TA needs initial list.
| 20.1. Development and publication of the simplified version of state budget and state budget execution reports | RF MOF | Open budget estimation and providing methodological support | X | X | X | X | X | X |  | X |  | Report on analysis of the level of openness of budget data in the Republic of Armenia at government and municipal levels
21.1 Publication of information on budget bids
21.2. Establishment of a platform (s) for discussing budget proposals with CSOs
|  | GIZ | Review and finalisation of Public Participation approaches; development of an e-participatory platform for state budget. | X | X | X | X |  |  | X |  |  | Approaches to public participation in state budgeting processes are finalised, e-participation platform is developed and functioning |  | The TA suggestion is detailed by GIZ
9. Arrears monitoring and management | Treasury operations including cash management and IFMIS | WB | Ongoing regional level support through PEMPAL regional project | X | X | X | X | X | X |  |  | knowledge sharing, learning about the good practices and experience of advanced countries | MoF relevant staff have access to knowledge related to the topic, have better understanding of international good practices | NO | The TA for the measure is suggested by WB. The measure wasn't included in MoF TA needs initial list. | The scope will be clarified by September
11. Public Debt Management | 28․1 Conformity of the RA Law "on Public Debt" to the standards applied by international financial institutions | ADB | 1.Review of existing laws, amendments and supplements |  | X | X | X |  |  | TBD | TBD |  | Report on review findings, recommendations and implementation roadap | NO | The scope of TA suggestion is limited compared to the ADB initial TA suggestion cutting off the training on DMFAS with UNCTAD, further training and advisory inputs
|  |  | 2.Organize workshops or FGDs to gather information |  |  | X | X
|  |  | 3.Submit a report on review findings and recommendations |  |  |  | X | X
|  |  | 4.Develop a roadmap with milestones and timelines |  |  |  | X | X
|  | WB | Update of Debt Management Performance Assessment (DeMPA), review of regulatory arrangements, review of governance arrangements for monitoring debt management function in the SOEs |  | X | X | X | X |  |  | X |  | Updated DeMPA in place, regulatory framwork is updated, governance arrangements over SOE debt management is reviewed | Possible overlaps WB/EU | WB initial TA suggestion didn't consider support for this measure implementation
|  | EU | The EU & World Bank will support GoA to update the 2013 Debt Management Performance Assessment (DeMPA), including a review of the relevant regulatory and operational arrangements of government debt management and efficiency of domestic debt markets (such as government bonds and T-bills). The EU & World Bank will support the development by GoA of procedures and regulations to support an efficient operational framework for government debt. The EU & World Bank will also review the governance arrangements for monitoring the debt of state-owned enterprises (SOEs) and support the Ministry of Finance in designing proposed processes for more effective monitoring and reporting of SOE borrowing operations. | [11 empty] | EU initial TA suggestion didn't consider support for this measure implementation
12. Public Sector Accounting | 31․1 Development of a methodology for consolidating financial statements | GIZ | Methodological and practical support to 10 municipalities on further APSAS implementation, incl. capacity development. | X | X | X | X | X |  | X |  |  | 10 municipalities are capable and capacitated to implement APSAS; Consolidation methodology is fully developed and ready for implementation; 2 advance enlarged municipalities (Jermuk and Stepanavan) and fully capable to prepare consolidated financial statements in line with APSAS; Service cost calculation methodology, including set up of management accounting system and its input in accounting system, is developd ​ | NO | The TA suggestion is detailed by GIZ
|  | WB | Potential support in developing a consolidation methodology |  | X | X | X |  |  |  | X |  | Consolidation methodology in place and ready to be applied |  | The TA suggestion is detailed by WB | The scope will be clarified by September
|  |  | Ongoing regional level support through PULSAR regional project | X | X | X | X | X | X |  |  | knowledge sharing, learning about the good practices and experience of advanced countries | MoF relevant staff have access to knowledge related to the topic, have better understanding of international good practices |  | The TA suggestion is detailed by WB
13. Regulation of corporate accounting and audit activity | 32․1 Completion of the necessary sub-legislative framework | RF MOF | Development of methodological instructions for preparation of financial statements by micro-organizations | X | X | [5 empty] | X |  | Guidelines on microenterprise accounting and financial reporting | NO | The TA for the measure is suggested by RF MOF. The measure wasn't included in MoF TA needs initial list.
|  | WB | Ongoing regional level support through STAREP regional project | X | X | X | X | X | X |  |  | knowledge sharing, learning about the good practices and experience of advanced countries | Members of the Public Oversight Board, members of the Chamber of Auditors and Accountants have access to knowledge related to the topics, have better understanding of international good practices | NO | This component is not a part of approved PFM strategy. The TA for the measures is suggested by WB. The measures weren't included in MoF TA needs initial list. | The scope will be clarified by September
|  |  | Strengthening of corporate accounting and auditing framework in Armenia | X | X | X | X | X |  |  | X |  | Capacity building, update of manuals and handbooks
14. Financial Management and Control of state organizations accountability of state non-commercial organizations (SNCOs) | 33․1 Development of a system of non-financial (productive) indicators for monitoring the activities of SNCOs | ADB | 1.Conduct diagnostics on selected/pilot SNCOs |  | X | X | X |  |  | TBD | TBD |  | (i) Report on diagnostic study on legal, regulatory and institutional framework; (ii) at least 1 workshop on FRA and FRM in the SNCO context; (iii) guidelines | NO | The TA suggestion is detailed by ADB | ADB -The scope clarification FRM/FMC
|  |  | 2.Provide policy guidance to MOF on strengthening legal, regulatory and institutional framework for implementation of fiscal risk assessment procedures |  | X | X | X | [6 empty] | NO
|  |  | 3.Conduct training workshops to relevant staff |  |  |  |  | X | [5 empty] | NO
|  |  | 4.Develop implementation guidelines for the selected/pilot SNCOs |  |  |  |  | X | X |  |  |  |  | NO
|  | GIZ | [12 empty] | The initial TA suggestion considers possible support on this measures, focus mainly on Community NCOs in the enlarged communities or big cities. But the measure is cut off from the present TA suggestion.
18. Financial management and control (FMC) | 37․1 Piloting of FMC system methodology | GIZ | Piloting of FMC manual and guideline in municipalities, development of a detailed action plan and capacity development measures for FMC introduction in municipalities. |  |  | X | X | X |  | X |  |  | Guidelineg for FMC introduction on local level developed and finalised based on results of FMC manual piloting on local level. Relevant capacities of municipalities on FMC introduction are developed | NO | The TA suggestion is detailed by GIZ
| 37․2 Adoption of FMC concept and FMC legal acts | GIZ | Review and finalisation of the draft FMC manual reflective to PB methodology (for both central and local levels) and based on it development of guideline for FMC introduction in communities | X | X | X |  |  |  | X |  |  | Draft FMC Manual is reviewed reflecting requirements of current PB methodology, and ready for piloting on central level (piloting is not covered) and local level (to be done by GIZ). Draft Guideline for FMC introduction on local level is developed | NO | The TA suggestion is detailed by GIZ
| 37․3 Introduction of FMC system in public sector organizations | GIZ | Piloting of FMC manual and guideline in municipalities, development of a detailed action plan and capacity development measures for FMC introduction in municipalities. |  |  | X | X | X |  | X |  |  | Guidelineg for FMC introduction on local level developed and finalised based on results of FMC manual piloting on local level. Relevant capacities of municipalities on FMC introduction are developed | NO | The TA suggestion is detailed by GIZ
19.Public sector internal audit | 38․1 Approval of external assessment methodology of internal audit quality | WB | Internal audit quality assessment |  |  |  | X | X |  |  | X |  | Updated internal audit external quality assessment methodology in place | NO | The TA suggestion is detailed by WB | The scope will be clarified by September
| 40.3 Development of performance auditing skills of internal auditors operating in RA public sector organizations | GIZ | Support in review and update of the overall IA methodological and legal frameworks; Modernisation of IA capacity building mechanisms (applicable for both local and central level); Review and establishment of a modern IA certification mechanism compliant to international standards; Assurance of independence of IA Units within LSGs and development of IA standardized approaches and tools for LSGs. | X | X | X | X |  |  | X |  |  | Legal and methodological frameworks of IA are updated, including IA standards (applicable for both central and local levels); IA capasity building mechanisms are reviewd and modernised (applicable for both central and local levels); New IA certification system is established (applicable for both central and local levels) Independence of IA in municipalities is assured through introduction of relevant legal provisions; IA procedures in municipalities are standardizes and comparable, based application of unifies approaches and tools (local level) | NO | The TA suggestion is detailed by GIZ
41․1 Elaboration of a program for the development of professional knowledge and skills of internal auditors
41․2 Optimization of continuous professional training courses for internal auditors
41․3. Development of an online information system for the continuous professional training of internal auditors
41․4 Review of public sector internal auditor qualification procedure
22.Public asset management | 44.1․Elaboration and approval of public assets management methodology and legal acts necessary for its introduction | GIZ | Support in improving and standardising municipal assets management at local level: analysis of the legal framework and development of two exemplary templates of decisions of the Municipal Council on (i) Mandatory annual inventory of municipality assets., and on (ii) Approving the annual programme for management of lands, buildings and constructions considered as municipal ownership. | X | X |  |  |  |  | X |  |  | Two exemplary templates of decisions of the Municipal Council on (i) "Mandatory annual inventory of municipality assets", and on (ii) "Annual programme for management of lands, buildings and constructions considered as municipal ownership" are developed and used for dicision making. | NO | The TA suggestion is detailed by GIZ
|  | RF MOF | Assistance in the activities for elaborating legislative acts and methodological materials necessary for the introduction of public asset management methodology | [7 empty] | X |  | To be agreed with the RA MOF | NO | The TA suggestion is detailed by RF MOF
|  | IMF2* | Possible complementary relationship between FAD and GIZ when providing TA on activities 44.2 and 45.1 using the model with respect to PBB. | [12 empty] | Support scope needs to be clarified
| 44.2 Implementation of training on asset management techniques in accordance with the approved legislation | GIZ | Support in improving and standardising municipal assets management at local level: analysis of the legal framework and development of two exemplary templates of decisions of the Municipal Council on (i) Mandatory annual inventory of municipality assets., and on (ii) Approving the annual programme for management of lands, buildings and constructions considered as municipal ownership. | X | X |  |  |  |  | X |  |  | Two exemplary templates of decisions of the Municipal Council on (i) "Mandatory annual inventory of municipality assets", and on (ii) "Annual programme for management of lands, buildings and constructions considered as municipal ownership" are developed and used for dicision making. | NO | The TA suggestion is detailed by GIZ. TA proposals submitted by the GIZ are only for local governments, do not cover the needs of the central government.
IMF2*
| 45.1 The definition on procedures for the sale, transfer, alienation process, and the right to use non-financial assets will be reviewed | IMF2* | [13 empty] | Support scope needs to be clarified
23. Public Investment Management (PIM) | 48.1. Practical application of PIM Manual in the budget process | GIZ1* | Development of a concept and manual on PIM in municipalities; Piloting and final introduction of PIM system in municipalities; Support in elaboration of relevant legal framework for introduction of PIM in municipalities; Development and conduction of capacity development measures on PIM. |  | X | X | X | X | X | X |  |  | PIM concept and manual for local level is developed and introduced in communities, relevant capacities of all stakeholders for PIM implementation are developed. | Possible overlaps between WB, USAID,AFD proposals | GIZ initial TA suggestions didn't include this measure. The latest was included in recent TA suggestion
|  | IMF3* | TA on PIM, which could also cover fiscal risks.The cooperation with ADB will focus on the monitoring of PPP projects implementation, periodic discussions with ADB and the presentation of the IMF assessments on the fiscal risks management system being developed. |  | X | X |  |  |  |  | IMF Staff and Experts |  | Further strengthening PIM legal and operational framework, integrating PIM into budget process |  | The TA suggestion is detailed by IMF | TBD_ADB /IMF coordination on i PPP option on PIM IMF support scope needs to be clarified
|  | ADB2* | 1.Review of existing laws and supplements on PPP and PIM |  | X | X |  |  |  | TBD | TBD |  | (i) implementation guidelines; (ii) conduct of at least 2 workshops on PIM Manual implementation on PPP option |  | The TA suggestion is detailed by ADB, cutting off further training on the next stages of the PIM function
|  |  | 2.Provide guidance in the establishment of methods of appraisal applicable to local (SNG) context, with the PPP option fully integrated to the PIM |  |  | X | X
|  |  | 3.Organize workshops or FGDs |  |  | X |  | X
|  |  | 4. Develop implementation guidelines specifically for PPP as integrated to the PIM framework |  |  |  | X | X
|  | WB | Capacity building and finalization of the PIM manual and handbook in accrodance wth the legislative framework | X | X | X | X | X | X |  | X |  | PIM manual and Handbook in place in accordance with the existing legislative framework |  | The TA suggestion is detailed by WB | The scope will be clarified by September
|  | AFD | Technical assistance to support the devlopment in processes |  | X | X | X | X | X | X |  |  | Support the process for prioritisation of public investment
| 49.1 Monitoring of public investment projects | GIZ1* | [11 empty] | Possible overlaps between WB, USAID,AFD proposals
ADB2*
|  | IMF3* | [13 empty] | Support scope needs to be clarified
26. Independence of the Audit Chamber and external audit of the government's annual financial statement | 53.2 Implementation of measures approved by the Chamber of Audit strategy for 2020-2023 | GIZ | Support to AC and MTAI in conduction of the financial, compliance and performance audits of the municipalities | X | X | X | X | X | X | X |  |  | Financial, compliance and performance audits are peiodically conducted in municipalities by Audit Chamber | NO | The TA for the measures is suggested by GIZ. The measures weren't included in MoF TA needs initial list.
| 54.1 Development and approval of capacity building programme for AC staff | GIZ | Further capacity building: trainings for the Audit Chamber to have certified auditors; on data analytics; specific on-job trainings for financial, compliance and performance audit | X | X | X | X | X | X | X |  |  | Audit Chamber staff members are certified as auditors; capacities of AC staff developed in the field of data analytics, financial, compliance and performance audits. | NO
| 54.2 Development of capacities and enhancement of professional skills of the AC staff | [12 empty] | NO
Government Finance Statistics and Fiscal Reporting |  | IMF | TA on developing comprehencive list of public sector units, TA and training on GFS for the central government |  | X | [5 empty] | IMF (funded by CCAMTAC) |  | (i) Comprehensive list of all public sector units, (ii) Compilation of GFS for budgetary central government using detailed CoA, (iii) Increased staff capacity to compile GFS | NO | This component is not a part of approved PFM strategy, but is proposed by the IMF as an issential part of the PFM reforms
|  |  | TA on extended GFS |  |  | X |  |  |  |  | IMF (funded by CCAMTAC) |  | Extension of annual GFS to include nonmarket SNCOs, LNCOs and JSCs compiled using detailed disaggregated data sources
Comply donor procedures with PFM procedures | Feasibility of using country systems in donor procedures | ADB | 1. Analyze implementation issues of donor-funded projects, and identify gaps between donor and national procedures for 1 or 2 donors (as pilot) | X | X |  |  |  |  | TBD | TBD |  | Report on findings and recommendations | NO | The TA suggestion is detailed by ADB | ADB-Timeline
|  | ADB | 2. Report on findings and recommendations |  | X |  |  |  |  | TBD | TBD |  |  | NO
* PIOs with identical numbers shows the cases when the same TA covers more than one measures, to avoid text repeat
USAID didn't submit the requisted information in proforma format. USAID envisages technical assistance project, called Financing Self Reliance, in late 2022.The project will focus on support in the public finance management area. Some of the potential areas for support are as follows: PIM Advisory/hands-on training for the application of the Public Investment Management Manual in the budget process Capacity building of the Ministry of Finance (MOF) and select line relevant Ministries' staff in monitoring of public investment projects Program Budgeting Technical assistance to MOF and select line ministries to develop budget programs in line with policies being carried out by existing strategic documents Piloting and testing program budgeting in MOF and select line Ministries Analysis of the existing methodology and its application Identification and regulation of practical issues related to program budgeting Technical assistance/capacity building in the evaluation of budget programs Internal audit Public Sector Internal Audit Continuous professional development for internal auditors National Assembly (NA) Technical assistance to the Budget Office, respective committees of NA, and parliament members to help them to improve understanding of the program budget process The areas of technical assistance will be finalized and agreed upon with the Ministry once USAID will have the winner of the competition for the Financing Self Reliance project.

## TA Needs & PIOProposals
Component of PFM Action Plan | Measure of PFM Action Plan | Deadline | Need for additional / new technical assistance | TA Proposals from PIOs
|  |  |  | GIZ | IMF | UNDP | USAID* | WB | ADB | RF MOF | AFD | EU/OECD/SIGMA | Status before PFM DCM | Status after PFM DCM | Notes
1. Macroeconomic and Budget Indicators Forecasting | Revenue forecasting methodology development | [8 empty] | Methodology of revenue forecasting development |  |  |  | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 1.2. Introduction and full-fledged launch of DSGE model(s) | [8 empty] | Completion of introduction of DSGE model |  |  |  | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 3.1. Implementation of measures aimed at development of capacities, enhancement of skills of the personnel | [8 empty] | Skills of application of the revenue forecasting model within RA MoF |  |  |  | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
3․ State revenue policy | 6․1 Outline of main directions of further reforms in the tax system based on economic development priorities and opportunities | [8 empty] | To be agreed with the RA MOF |  |  |  | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 7.1 Elaboration of the RA draft law "On Making Amendments to the RA Tax Code" | [7 empty] | Proposed amendments to the Tax Code (i) unified alternative tax system to replace the turnover tax regime, (ii) mnitoring and reporting framework for tax expenditures, and (iii) thin capitalization rules (based on best international practices). |  |  |  |  | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 8․1 Elaboration of the RA draft law "On Making Amendments to the Tax Code of the Republic of Armenia" | [7 empty] | Proposed amendments to the Tax Code (i) unified alternative tax system to replace the turnover tax regime, (ii) mnitoring and reporting framework for tax expenditures, and (iii) thin capitalization rules (based on best international practices). |  |  |  |  | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
4. Revenue Transparency and Compliance | 12․1.Assess tax potential and tax gap for three major types of taxes (VAT, profit tax, income tax) |  |  |  | TA on calculation of VAT Gap | [8 empty] | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 15.1. Modernize analytical and control tools and improve capacities of tax authority |  |  |  | TA on implementing CRM (Compliance risk managment) TA on audits using IAM (Identity and Access Management) TA on implementing Universal PIT Declaration TA on mobilizing taxes from multinational enterprises | [8 empty] | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
6. MTEF process, budget disciplinary and transparency | 19.1. Developing legal framework and methodology for a unified procedure of MTEF and annual budget development |  |  |  | 1. TA on piloting the revised mandatory/ discretionary distinction 2.TA on budget preparation (CCAMTAC) | [8 empty] | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 20.1. Development and publication of the simplified version of state budget and state budget execution reports | [8 empty] | Open budget estimation and providing methodological support |  |  |  | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 21.1 Publication of information on budget bids | [8 empty] | Open budget estimation and providing methodological support |  |  |  | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 21.2. Establishment of a platform (s) for discussing budget proposals with CSOs |  |  | Review and finalisation of Public Participation approaches; development of an e-participatory platform for state budget. | [5 empty] | Open budget estimation and providing methodological support |  |  |  | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
11. Public Debt Management | 28․1 Conformity of the RA Law "on Public Debt" to the standards applied by international financial institutions | December, 2022 | Assistance to elaboration activities of the new RA draft Law "On Making Amendments and Supplements" to the RA Law "On Public Debt" | - | - | - | - | Update of Debt Management Performance Assessment (DeMPA), review of regulatory arrangements, review of governance arrangements for monitoring debt management function in the SOEs | 1.Review of existing laws, amendments and supplements 2.Organize workshops or FGDs to gather information 3.Submit a report on review findings and recommendations 4.Develop a roadmap with milestones and timelines | - | - | The EU & World Bank will support GoA to update the 2013 Debt Management Performance Assessment (DeMPA), including a review of the relevant regulatory and operational arrangements of government debt management and efficiency of domestic debt markets (such as government bonds and T-bills). The EU & World Bank will support the development by GoA of procedures and regulations to support an efficient operational framework for government debt. The EU & World Bank will also review the governance arrangements for monitoring the debt of state-owned enterprises (SOEs) and support the Ministry of Finance in designing proposed processes for more effective monitoring and reporting of SOE borrowing operations. | Overlap possibility | Full coverage
12. Public Sector Accounting | 31․1 Development of a methodology for consolidating financial statements | 2022-2023 | Development of a methodology for consolidating financial statements | Methodological and practical support to 10 municipalities on further APSAS implementation, incl. capacity development. | - | - | - | Potential support in developing a consolidation methodology .Ongoing regional level support through PULSAR regional project | - | - | - | - | Partial coverage | Partial coverage | The scope of WB support will be clarified by September
13. Regulation of corporate accounting and audit activity | 32․1 Completion of the necessary sub-legislative framework | [6 empty] | Ongoing regional level support through STAREP regional project .Strengthening of corporate accounting and auditing framework in Armenia |  | Development of methodological instructions for preparation of financial statements by micro-organizations |  |  |  | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
14. Financial Management and Control of state organizations accountability of state non-commercial organizations (SNCOs) | 33․1 Development of a system of non-financial (productive) indicators for monitoring the activities of SNCOs | 2020-2023 | Review of SNCOs fiduciary control concept and model to bring it in line with the current requirements of the reforms in the field of PFM |  | - | - | - | - | 1.Conduct diagnostics on selected/pilot SNCOs 2.Provide policy guidance to MOF on strengthening legal, regulatory and institutional framework for implementation of fiscal risk assessment procedures 3.Conduct training workshops to relevant staff 4.Develop implementation guidelines for the selected/pilot SNCOs | - | - | - | Partial coverage | Partial coverage
|  |  | Development of a system of standard non-financial (output) indicators for monitoring and evaluation of financial and economic activities of SNCOs |  | - | - | - | - |  | - | - | -
|  |  | Support for the introduction of fiduciary control system of SNCOs |  | - | - | - | - |  | - | - | -
18. Financial management and control (FMC) | 37․1 Piloting of FMC system methodology | December, 2021 | Support to FMC system methodology piloting and review activities | Piloting of FMC manual and guideline in municipalities, development of a detailed action plan and capacity development measures for FMC introduction in municipalities. | - | - | - | - | - | - | - | - | Partial coverage | Partial coverage | Central level is not covered or covered partially
| 37․2 Adoption of FMC concept and FMC legal acts | 2022-2023 | Elaboration/revision of FMC concept and legal acts | Review and finalisation of the draft FMC manual reflective to PB methodology (for both central and local levels) and based on it development of guideline for FMC introduction in communities | - | - | - | - | - | - | - | - | Partial coverage | Full coverage
| 37․3 Introduction of FMC system in public sector organizations | from 2022 | Elaboration of FMC system introduction measures plan | Piloting of FMC manual and guideline in municipalities, development of a detailed action plan and capacity development measures for FMC introduction in municipalities. | - | - | - | - | - | - | - | - | Partial coverage | Partial coverage | Central level is not covered or covered partially
|  |  | Training needs assessment of specialists involved in the FMC system and elaboration of training programs / modules / | [10 empty] | Partial coverage | Needs assessments and training programs are not covered
19.Public sector internal audit | 38․1 Approval of external assessment methodology of internal audit quality | December, 2021 | Review of methodology of external assessment of internal audit quality | - | - | - | Public Sector Internal Audit Continuous professional development for internal auditors | Internal audit quality assessment | - | - | - | - | Partial coverage | Partial coverage | The scope of WB support will be clarified by September
| 38․2 Implementation of external assessment of internal audit quality in public sector organizations | 2021-2023 | Assistance in pilot risk assessment of RA public sector organizations according to the internal audit quality assessment manual | - | - | - | - | - | - | - | - | - | No proposal | No proposal
| 40․1 Approval of performance auditing methodology | 2021-2022 | Review of performance audit manual/guideline | - | - | - | - | - | - | - | - | - | No proposal | No proposal
| 40.3 Development of performance auditing skills of internal auditors operating in RA public sector organizations | 2021-2023 | Elaboration of training program/modules on performance audit | Support in review and update of the overall IA methodological and legal frameworks; Modernisation of IA capacity building mechanisms (applicable for both local and central level); Review and establishment of a modern IA certification mechanism compliant to international standards; Assurance of independence of IA Units within LSGs and development of IA standardized approaches and tools for LSGs. | - | - | - | - | - | - | - | - | Full coverage | Full coverage
| 41․1 Elaboration of a program for the development of professional knowledge and skills of internal auditors | December, 2021 | Assessment of capacity and professional needs of internal auditors and elaboration of development plan for their capacity building |  | - | - | - | - | - | - | - | - | Full coverage | Full coverage
| 41․2 Optimization of continuous professional training courses for internal auditors | 2021-2023 | Elaboration of suggestions/concept for optimization of continuous professional training courses for internal auditors |  | - | - | - | - | - | - | - | - | Full coverage | Full coverage
| 41․3. Development of an online information system for the continuous professional training of internal auditors | 2021-2022 | Design and elaboration of an online information system for the continuous professional training of internal auditors |  | - | - | - | - | - | - | - | - | No proposal | Partial coverage | Online information system is not covered
| 41․4 Review of public sector internal auditor qualification procedure | December, 2022 | Elaboration of a concept for review of public sector internal auditor qualification procedure |  | - | - | - | - | - | - | - | - | Full coverage | Full coverage
2 Fiscal risks accountability | 4․1 Expanding the coverage of fiscal risk assessment, improving the methodology | 2020-2023 | Assistance in expanding fiscal risk assessment coverage (support for elaboration of fiscal risk assessment methodology and guidelines and for their application form natural and man-made disasters, litigation against the state, environmental liabilities and financial system) | - | TA on fiscal risks, which could also cover PIM, monitoring the progress of the activities within the Stand-By Agreement (SBA) program discussions.On the basis that the ADB will continue to provide TA on activity 4.1, IMF could continue monitoring the progress of the activity within the Stand By Agreement (SBA) program discussions, Support plans for the near term: (i) Mission on fiscal risks, which could also cover PIM (HQ) (ii) STX mission on fiscal risks (DG Near)(iii) STX mission on supporting implementation of (CRM) strategy and sectoral compliance improvement plans This action is related to revenue administration | - | - | - | 1.Provide training support and advisory inputs on Fiscal Risk Assessment and on adoption of FRM Framework roadmap 2.Develop methodological guidelines | The assitance is providing now | - | - | Full coverage | Full coverage
| 5․1 Capacity building | 2020-2023 | Support for professional capacity building of the the staff of the RA MoF in the field of fiscal risk management (on-site and online training ) | - | - | - | - | - | 1.Provide training support and advisory inputs on Fiscal Risk Assessment and on adoption of FRM Framework roadmap 2.Develop methodological guidelines |  | - | - | Full coverage | Full coverage
20. Central Harmonization Unit (CHU) | 42․1 CHU staff recruitment and capacity building | 2019-2021 | Staff and capacity needs assessment required for the CHU performance of functions and elaboration of a staff capacity development plan/roadmap for the capacity building | - | - | - | - | - | - | - | - | - | Partial coverage | No proposal
21. Financial and Budgetary Supervision | 43․1․ Review, update of financial-budgetary supervision legislation, elaboration of new methodology for implementation of financial-budgetary supervision | 2020-2021 | Financial and Budgetary Supervision- Elaboration of a new methodology for risk-based inspections | - | - | - | - | - | - | - | - | - | Partial coverage | No proposal
| 43.2 Capacity building of specialists in the field of financial-budgetary supervision | 2022-2023 | Assessment of capacity building of financial and budgetary supervision specialists and elaboration of development plan/roadmap | - | - | - | - | - | - | - | - | - | Full coverage | No proposal
| 43․3 Availability of database necessary for risk assessment | 2020-2023 | Development of an automated risk assessment system | - | - | - | - | - | - | - | - | - | Full coverage | No proposal
22.Public asset management | 44.1․Elaboration and approval of public assets management methodology and legal acts necessary for its introduction | 2020-2022 | Assistance in the activities for elaborating legislative acts and methodological materials necessary for the introduction of public asset management methodology | Support in improving and standardising municipal assets management at local level: analysis of the legal framework and development of two exemplary templates of decisions of the Municipal Council on (i) Mandatory annual inventory of municipality assets., and on (ii) Approving the annual programme for management of lands, buildings and constructions considered as municipal ownership. | Possible complementary relationship between FAD and GIZ when providing TA on activities 44.2 and 45.1 using the model with respect to PBB | - | - | - | - | Assistance in the activities for elaborating legislative acts and methodological materials necessary for the introduction of public asset management methodology | - | - | Overlap possibility | Full coverage
| 44.2 Implementation of training on asset management techniques in accordance with the approved legislation | 2020-2022 | Training needs assessment in terms of public asset management techniques |  | - | - | - | - | - | - | - | - | Partial coverage | Partial coverage | Central level is not covered or covered partially
| 45.1 The definition on procedures for the sale, transfer, alienation process, and the right to use non-financial assets will be reviewed. | 2022-2023 | Elaboration of procedures for the sale, transfer, alienation, and use of non-financial assets |  | - | - | - | - | - | To be agreed with the RA MOF | - | - | Overlap possibility | Partial coverage
23. Public Investment Management (PIM) | 48.1. Practical application of PIM Manual in the budget process | December, 2022 | Support in the development and localization of budgetary processes arising from the PIM manual | Development of a concept and manual on PIM in municipalities; Piloting and final introduction of PIM system in municipalities; Support in elaboration of relevant legal framework for introduction of PIM in municipalities; Development and conduction of capacity development measures on PIM. | TA on PIM, which could also cover fiscal risks using the model with respect to PBB. PIM follow ups: Assist with further strengthening PIM legal and operational framework, integrating PIM into budget process in collaboration with other development partners.The cooperation with ADB will focus on the monitoring of PPP projects implementation in the context of IMF supported Stand-by program, periodic discussions with ADB and the presentation of the IMF assessments on the fiscal risks management system being developed. | - | Advisory/hands-on training for the application of the Public Investment Management Manual in the budget process Capacity building of the Ministry of Finance (MOF) and select line relevant Ministries' staff in monitoring of public investment projects | Capacity building and finalization of the PIM manual and handbook in accrodance wth the legislative framework | 1.Review of existing laws and supplements on PPP and PIM 2.Provide guidance in the establishment of methods of appraisal applicable to local (SNG) context, with the PPP option fully integrated to the PIM 3.Organize workshops or FGDs 4. Develop implementation guidelines specifically for PPP as integrated to the PIM framework | - | Support the process for prioritisation of public investment | - | Overlap possibility | Overlap possibility | Possible overlaps between WB, USAID,AFD proposals
| 49.1 Monitoring of public investment projects | 2022-2023 | Elaboration / review of business processes in the RA Ministry of Finance in accordance with the PIM manual |  |  | - |  | - |  |  |  | - | Overlap possibility | Overlap possibility | Possible overlaps between WB, USAID,AFD proposals
5. Program budgeting and strategic planning | 16․1․ Review/develop budget programs in line with policies being carried out by existing strategic documents | 2020-2022 | Study / evaluation of compliance of budget programs with the policies defined by the strategic documents | - | TA on aligning budgetary framework with the strategic planning framework. Assist with aligning budgetary framework with the strategic planning framework TA will be provided within a continuation of complementary TA relationship with GIZ on PBBContinuation of complementary TA relationship with GIZ on PBB" is not an action | Support MoF in studying / evaluating the compliance of budget programs with the policies defined by the strategic documents | Technical assistance to MOF and select line ministries to develop budget programs in line with policies being carried out by existing strategic documents Piloting and testing program budgeting in MOF and select line Ministries Analysis of the existing methodology and its application Identification and regulation of practical issues related to program budgeting Technical assistance/capacity building in the evaluation of budget programs | - | - | Analysis of strategic documents with a view of identifying linkages with budget programs of line ministries | - | - | Overlap possibility | Overlap possibility | Possible overlaps between IMF,UNDP proposals
|  |  | Support to state bodies for activities in reviewing policy documents and budget programs (and passports) and their compliance | - |  |  |  | - | - |  | - | - | Overlap possibility
| 16․2 Identification and regulation of practical issues related to program budgeting existing methodology and its application | 2020-2022 | Assistance in implementing measures to improve the program budgeting methodology | Support to MTAI and MOF in making PB mandatory for local level (based on similar experience from central level): legal amendments, final review and harmonisation of methodologies, creation of a cooperation platform between all stakeholders. | TA on program budgeting framework (classification, evaluation guidelines).Assist with aligning budgetary framework with the strategic planning framework TA will be provided within a continuation of complementary TA relationship with GIZ on PBB.Support further improvement in program budgeting framework (classification, evaluation guidelines). The most recent PFM short-term expert (STX) mission by the IMF’s Fiscal Affairs Department (FAD) addressed outstanding PBB issues. It could be logical for FAD to undertake the further follow-up TA on the PBB-related activity 16.2. In recent years, GIZ’s TA on PBB has complemented the IMF’s TA, by funding a local consultant focusing on training and detailed procedures. A continuation of this complementary TA relationship could be logical. | - | - | - | - | Review and analysis of the methodological guidelines for the development of sectoral strategies from the perspective of program budgeting, | - | - | Overlap possibility | Full coverage
| 16․3․ Measures for human resources development | 2020-2023 | In the context of program budgeting, study of the current functions and capacities of the RA MoF budget process organization department and elaboration of a roadmap for their improvement | - | TA on program budgeting framework (classification, evaluation guidelines).The most recent PFM short-term expert (STX) mission by the IMF’s Fiscal Affairs Department (FAD) addressed outstanding PBB issues. It could be logical for FAD to undertake the further follow-up TA on the PBB-related activity 16.3. In recent years, GIZ’s TA on PBB has complemented the IMF’s TA, by funding a local consultant focusing on training and detailed procedures. A continuation of this complementary TA relationship could be logical. | - | - | - | - |  | - | - | Overlap possibility | Full coverage
|  |  | Evaluation of existing capabilities of state bodies in terms of implementation of program budgeting requirements and elaboration of their development plan | - | - | - | - | - | - | - | - | - |  | Full coverage
| 17․2․ Introduce a process of regular evaluation of budget programs | December, 2023 | Assistance in the activities for project monitoring and evaluation methodology testing in state bodies, as well as introduction of these processes implementation of these processes | Piloting and finalisation of the concept and methodology on Programme Monitoring and Evaluation, including also capacity development activities. | - | - | - | - | - | - | - | - | Full coverage | Full coverage
25. Control of the financial-budgetary sphere by the National Assembly | 52.1 Institutional-internal capacity building of the budget office | 2020-2023 |  |  |  |  | Technical assistance to the Budget Office, respective committees of NA, and parliament members to help them to improve understanding of the program budget process | [6 empty] | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 52.2 Capacity building of NA deputies and experts of committees | 2020-2023 |  |  |  |  | Technical assistance to the Budget Office, respective committees of NA, and parliament members to help them to improve understanding of the program budget process | [6 empty] | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
26. Independence of the Audit Chamber and external audit of the government's annual financial statement | 53.2 Implementation of measures approved by the Chamber of Audit strategy for 2020-2023 |  |  | Support to AC and MTAI in conduction of the financial, compliance and performance audits of the municipalities | [9 empty] | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 54.1 Development and approval of capacity building programme for AC staff |  |  | Further capacity building: trainings for the Audit Chamber to have certified auditors; on data analytics; specific on-job trainings for financial, compliance and performance audit | [9 empty] | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
| 54.2 Development of capacities and enhancement of professional skills of the AC staff | [12 empty] | TBD | The TA suggestion formulated by PIO needs to be discussed with responsibilities
Government Finance Statistics and Fiscal Reporting |  |  |  |  | TA on developing comprehencive list of public sector units, TA and training on GFS for the central government.TA on extended GFS | [8 empty] | Full coverage
Comply donor procedures with PFM procedures | Comply donor procedures with PFM procedures |  | Study of donor procedures in PFM sector and mapping the differences with the national PFM procedures, development of roadmaps for the application of national procedures by donors | - | - | - | - | - | 1. Analyze implementation issues of donor-funded projects, and identify gaps between donor and national procedures for 1 or 2 donors (as pilot) | - | - | - |  | Full coverage
* USAID envisages technical assistance project, called Financing Self Reliance, in late 2022.

## TA Needs - Possible Ovelaps
PFM Area | TA needs | GIZ | IMF | UNDP | WB | USAID* | ADB | EU | RF MoF | AFD
Public Investment Management (PIM) | Elaboration and revision of budgetary processes arising from the PIM manual | x |  |  | x |  |  |  |  | X
Strategic Planning (SP) | Study / evaluation of budget programs’ compliance with the policies defined by the strategic documents |  | x | x |  |  |  |  | x
| Evaluation of capacities of state bodies in terms of implementation of PB requirements and elaboration of capacity improvement plan | x | X
* USAID envisages technical assistance project, called Financing Self Reliance, in late 2022.

## TA Needs- Partial&Not Cover
PFM Area | TA needs | Partially covered | Not covered | Capacities | Automation | Piloting | Regulation
Internal Audit (IA) | Revision of performance audit manual/guideline |  | X |  |  |  | X
| Assistance in pilot risk assessment of public sector organizations according to the internal audit quality assessment manual |  | X |  |  | X
| Design and elaboration of an online software for the continuous professional training of internal auditors |  | X |  | X
Financial-budgetary Oversight (FBO) | Elaboration of a new methodology for risk-based FBO inspections |  | X
| Development of an automated risk assessment system for FBO |  | X |  | X
Financial Management and Control (FMC) | Training needs assessment of specialists involved in the FMC and elaboration of training programs / modules* | X |  | X
| Piloting and revision of FMC methodology* | X |  |  |  | X
Public Asset Management (PAM) | Assessment of training needs on PAM techniques * | X |  | X
* TA proposals submitted by the GIZ are only for local governments, do not cover the needs of the central government.